## Gantt Chart
Task name | Task Allocation | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Team Organistation | N/a
Client Interview | All group | bar: Week 3 to Week 12
Requirement Document | Aliya | bar: Week 3 to Week 6
Work plan (e.g. Gantt Chart) | Adam, Aliya | bar: Week 3 to Week 6
Meeting Minutes | Zainah | Week 5: Re-made template
Requirement Specification & prototype Interim documentation | Group | bar: Week 3 to Week 6
Introduction | Zainah | bar: Week 3 to Week 6
Team Expertise | Yaasmeen | bar: Week 3 to Week 6
Rational (Reasoning) of topic choice | Bilal | bar: Week 3 to Week 6
Literature Review (similar exisitng solutions, tools, equipment) | Shuaib | bar: Week 3 to Week 6
Functional & Non-functional requirements | Adam, Azeem | bar: Week 3 to Week 6
Data description | Bilal | bar: Week 3 to Week 6
User Interface | Aliya, Humairah, Yaasmeen | bar: Week 3 to Week 6
LSEPI (ethics) | Humairah | bar: Week 3 to Week 6
Risk & economic aspects | Humairah | bar: Week 3 to Week 6
Peer Review | Yaasmeen | bar: Week 3 to Week 6
Describe Tasks Allocated | Yaasmeen | bar: Week 3 to Week 6
Achivements | Yaasmeen | bar: Week 3 to Week 6
Scoring the contribution | Yaasmeen | bar: Week 3 to Week 6
Code associated with the Interim Prototype | Group | bar: Week 3 to Week 7
Key:
[12 empty] | #601700 | Not started
[12 empty] | #008080 | In Progress
[12 empty] | #1E3950 | Completed
[12 empty] | #006030 | N/A